## Project Management
Task/Ticket | Priority | Status | Start date | End date | Milestone | Notes
Define Project Purpose | High | Completed | 2025-07-29 | 2025-08-02 | Project Definition | Write a short project statement. Document why this project matters (portfolio value, healthcare insights, technical demonstration).
Define Scope | Medium | Completed | 2025-07-30 | 2025-08-02 | Project Definition | Decide which datasets to use (e.g., latest year only vs. multi-year) Choose focus areas: hospital type, Medicare vs. Medicaid Document exclusions (columns, hospitals, years that won’t be used)
Define Deliverables | Medium | Completed | 2025-07-31 | 2025-08-03 | Project Definition | Specify outputs: Data cleaning scripts Exploratory data analysis notebook Dashboard (Power BI/Tableau) Final report / case study write-up Draft success criteria (what would make the project “done”)
Define Stakeholders/Audience | High | Completed | 2025-07-30 | 2025-08-02 | Project Definition | Identify who this project is for: Portfolio recruiters/hiring managers, Data analyst peers for feedback, Write notes on tailoring the project (clarity, storytelling, visuals).
Define Key Questions to Answer | High | Completed | 2025-07-30 | 2025-08-05 | Project Definition | Document these questions in a “Research Questions” section.
Define Metrics & KPIs | High | Completed | 2025-07-30 | 2025-08-05 | Project Definition | List the main measures you’ll calculate
Define Timeline & Milestones | Medium | Completed | 2025-08-07 | 2025-08-14 | Project Definition | Break down the project into phases (Setup → Cleaning → Analysis → Visualization → Final Report) Assign tentative due dates for each milestone.
Identify Data Sources | High | Completed | 2025-08-15 | 2025-08-18 | Data Acquisition | Research and confirm official source for hospital provider cost report data. Document where data is stored: https://data.cms.gov/provider-compliance/cost-report/hospital-provider-cost-report Update frequency: According to data source, typically updates every 12 months, or data update frequency is Annually Formats available: CSV File Only
Download Raw Data | High | Completed | 2025-08-17 | 2025-08-18 | Data Acquisition | Download the most recent Hospital Provider Cost Report dataset. If needed, download multiple years for trend analysis. Save raw data files into a /data/raw folder (keep unaltered).
Collect Metadata & Documentation | High | Completed | 2025-08-17 | 2025-08-18 | Data Acquisition | Download the data dictionary/technical documentation from CMS, Review field definitions, Save in a /docs folder for reference.
Version Control Setup | Medium | Completed | 2025-08-17 | 2025-08-20 | Data Acquisition | Create GitHub repository for all files: https://github.com/jcao-portfolio/hospital-provider-cost-data-analysis Add raw data files to .gitignore if they are too large, Store metadata + links in README or a separate log file, Create a changelog for which dataset version/date you’re using
File Format Verification | Medium | Completed | 2025-08-17 | 2025-08-20 | Data Acquisition | Check file format (CSV, Excel), Open a sample in Python/Excel to confirm readability. Note any formatting quirks (headers, encoding, delimiters).
Initial Data Import | Medium | Completed | 2025-08-17 | 2025-08-18 | Data Acquisition | Write a small script to load the dataset into Pandas/SQL. Verify row counts and column names match the documentation.
Data Source Cross-check | Medium | Completed | 2025-08-17 | 2025-08-18 | Data Acquisition | Identify if other related datasets should be acquired. Document which datasets are in scope
Storage & Organization | Medium | Completed | 2025-08-17 | 2025-08-18 | Data Acquisition | Create project folder structure
Preparing the Environment | High | Completed | 2025-08-21 | 2025-08-26 | Data Preparation | Add a section in the jupyter notebook data analysis for required libraries to import, as well as to read the data set
Data Source & Preparation | Medium | Completed | 2025-08-21 | 2025-08-26 | Data Preparation | Add a section in the jupyter notebook data analysis for where the dataset comes from, how was the data separated/combined, what you did to simplify the analysis, if there were any preprocessed scripts used to merge the data together
Data Exploration | High | Completed | 2025-08-22 | 2025-08-27 | Data Preparation | Add a section in the jupyter notebook data analysis to see how the data looks, by displaying the first and last 5 records of the dataset. Also note what the dataset contains, such as categorical, geographical, or numerical variables. What does each record (row) represent?
Data Validation | Medium | Completed | 2025-08-23 | 2025-08-27 | Data Preparation | Add a section in the jupyter notebook data analysis for descriptive statistics of the dataset, shape, additional information of number of records and columns, column names and data types, count of missing values per column, the percentage of missing values, and note potential outliers
Conceptualize the Data | Medium | Completed | 2025-08-26 | 2025-08-27 | Data Preparation | In order to understand and conceptualize the data, you first need to identify three main things: What is the grain of the table? What are the key metrics? What are the key dimensions?
Locate Solvable Issues | Medium | In progress | 2025-08-26 | 2025-08-28 | Data Preparation | Identify fixable problems (missing values, duplicates, outliers, formatting)
Evaluate Unsolvable Issues | Medium | In progress | 2025-08-26 | 2025-08-29 | Data Preparation | Flag issues that can’t be resolved (bias, missing context, incomplete records) and assess impact
Augment and Improve dataset | Medium | In progress | 2025-08-26 | 2025-08-29 | Data Preparation | Enrich data with external sources, create new variables, or engineer features
Note and Document Issues | Medium | In progress | 2025-08-26 | 2025-08-30 | Data Preparation | Record all changes, assumptions, and decisions for transparency and reproducibility